## Product Backlog
ID | Hạng mục | Chi tiết (Wiki URL) | Độ ưu tiên | Ước tính giá trị | Ước tính khối lượng công viêc ban đầu | Ước lượng mới công việc còn lại theo Sprint... |  |  |  |  | Thực hiện chuẩn | 32 | 24 | 16 | 8 | 0
[6 empty] | S1 | S2 | S3 | S4 | S5 | Thực hiện hiện tại | 32 | 32 | 32 | 32 | 32
1 | As admin and customer, I want to manage membership | User can using | Strong |  | 4 | 4 | 4 | 4 | 4 | 4
2 | As admin I want to manage users | Admin can manage user | Weak |  | 4 | 4 | 4 | 4 | 4 | 4
3 | As admin, I want to manage products | Admin can manage user | Medium |  | 4 | 4 | 4 | 4 | 4 | 4
4 | As admin, I want to manage orders | Admin can manage user | Strong |  | 4 | 4 | 4 | 4 | 4 | 4
5 | As admin, I want to manage shipping | Admin can manage user | Medium |  | 4 | 4 | 4 | 4 | 4 | 4
6 | As admin, I want to manage comments | Admin can manage user | Medium |  | 4 | 4 | 4 | 4 | 4 | 4
7 | As customer, I want to see more products. | Customer can see products | Strong |  | 4 | 4 | 4 | 4 | 4 | 4
8 | As customer, I want to buy products. | Customer can buy product | Strong |  | 4 | 4 | 4 | 4 | 4 | 4
9 | As customer, I want to see history orders | Customer can see history orders | Medium |  | 4 | 4 | 4 | 4 | 4 | 4
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
Note on C1: Mô tả chi tiết về luồng thực hiện chức năng --sinhnx Tue Oct 18 2011 18:13:48 GMT+0700 (SE Asia Standard Time)
Note on F1: Chọn một trong 3 giá trị: [Not Started] [In progress] [Complete] --sinhnx Tue Oct 18 2011 18:14:07 GMT+0700 (SE Asia Standard Time)

## Sprint 1
Hạng mục trong Project Backlog | Công việc trong Sprint | Người thực hiện | Ước tính khối lượng công việc ban đầu | Ước lượng mới về công việc còn lại | [5 empty] | Công việc hiện tại | 87 | 81 | 81 | 81 | 81 | 85 | 85
|  |  |  | T2 | T3 | T4 | T5 | T6 | T7 | Thực hiện chuẩn | 87 | 72.5 | 58 | 43.5 | 29 | 14.5 | 0
| Deploying MVC model | Nam, Thăng | 6 |  |  |  |  | 4 | 4 |  | ID
As admin and customer, I want to manage membership | UseCase | Nam, Thăng, Thắng, Tuấn,Quảng | 3 | 3 | 3 | 3 | 3 | 3 | 3
| ERD Diagram | Nam, Thăng, Thắng, Tuấn | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Database design | Nam,Thăng | 3 | 3 | 3 | 3 | 3 | 3 | 3
As admin I want to manage users | UseCase | Nam, Thăng, Thắng, Tuấn,Quảng | 3 | 3 | 3 | 3 | 3 | 3 | 3
| ERD Diagram | Nam, Thăng, Thắng, Tuấn | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Database design | Nam,Thăng | 3 | 3 | 3 | 3 | 3 | 3 | 3
As admin, I want to manage products | UseCase | Nam, Thăng, Thắng, Tuấn,Quảng | 3 | 3 | 3 | 3 | 3 | 3 | 3
| ERD Diagram | Nam, Thăng, Thắng, Tuấn | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Database design | Nam,Thăng | 3 | 3 | 3 | 3 | 3 | 3 | 3
As admin, I want to manage orders | UseCase | Nam, Thăng, Thắng, Tuấn,Quảng | 3 | 3 | 3 | 3 | 3 | 3 | 3
| ERD Diagram | Nam, Thăng, Thắng, Tuấn | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Database design | Nam,Thăng | 3 | 3 | 3 | 3 | 3 | 3 | 3
As admin, I want to manage shipping | UseCase | Nam, Thăng, Thắng, Tuấn,Quảng | 3 | 3 | 3 | 3 | 3 | 3 | 3
| ERD Diagram | Nam, Thăng, Thắng, Tuấn | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Database design | Nam,Thăng | 3 | 3 | 3 | 3 | 3 | 3 | 3
As admin, I want to manage comments | UseCase | Nam, Thăng, Thắng, Tuấn,Quảng | 3 | 3 | 3 | 3 | 3 | 3 | 3
| ERD Diagram | Nam, Thăng, Thắng, Tuấn | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Database design | Nam,Thăng | 3 | 3 | 3 | 3 | 3 | 3 | 3
As customer, I want to see more products. | UseCase | Nam, Thăng, Thắng, Tuấn,Quảng | 3 | 3 | 3 | 3 | 3 | 3 | 3
| ERD Diagram | Nam, Thăng, Thắng, Tuấn | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Database design | Nam,Thăng | 3 | 3 | 3 | 3 | 3 | 3 | 3
As customer, I want to buy products | UseCase | Nam, Thăng, Thắng, Tuấn,Quảng | 3 | 3 | 3 | 3 | 3 | 3 | 3
| ERD Diagram | Nam, Thăng, Thắng, Tuấn | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Database design | Nam,Thăng | 3 | 3 | 3 | 3 | 3 | 3 | 3
As customer, I want to see history order | UseCase | Nam, Thăng, Thắng, Tuấn,Quảng | 3 | 3 | 3 | 3 | 3 | 3 | 3
| ERD Diagram | Nam, Thăng, Thắng, Tuấn | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Database design | Nam,Thăng | 3 | 3 | 3 | 3 | 3 | 3 | 3
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Note on B1: Một chức năng được chia nhỏ ra thành các phần nhỏ hơn gọi là tác vụ. --sinhnx Tue Oct 18 2011 17:33:20 GMT+0700 (SE Asia Standard Time)
Note on C1: Người thực hiện tác vụ này --sinhnx Tue Oct 18 2011 17:33:05 GMT+0700 (SE Asia Standard Time)
Note on D1: Thời gian dự kiến hoàn thành (tính theo giờ) --sinhnx Tue Oct 18 2011 18:18:20 GMT+0700 (SE Asia Standard Time)

## Sprint 2
Hạng mục trong Project Backlog | Công việc trong Sprint | Người thực hiện | Ước tính khối lượng công việc ban đầu | Ước lượng mới về công việc còn lại | [5 empty] | Công việc hiện tại | 84 | 78 | 78 | 78 | 78 | 82 | 82
|  |  |  | T2 | T3 | T4 | T5 | T6 | T7 | Thực hiện chuẩn | 84 | 70 | 56 | 42 | 28 | 14 | 0
| Deploying MVC model | Nam, Thăng | 6 |  |  |  |  | 4 | 4
As admin and customer, I want to manage membership | UseCase | Nam, Thăng, Thắng, Tuấn,Quảng | 3 | 3 | 3 | 3 | 3 | 3 | 3
| ERD Diagram | Nam, Thăng, Thắng, Tuấn | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Database design | Nam,Thăng | 3 | 3 | 3 | 3 | 3 | 3 | 3
As admin I want to manage users | UseCase | Nam, Thăng, Thắng, Tuấn,Quảng | 3 | 3 | 3 | 3 | 3 | 3 | 3
| ERD Diagram | Nam, Thăng, Thắng, Tuấn | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Database design | Nam,Thăng | 3 | 3 | 3 | 3 | 3 | 3 | 3
As admin, I want to manage products | UseCase | Nam, Thăng, Thắng, Tuấn,Quảng | 3 | 3 | 3 | 3 | 3 | 3 | 3
| ERD Diagram | Nam, Thăng, Thắng, Tuấn | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Database design | Nam,Thăng | 3 | 3 | 3 | 3 | 3 | 3 | 3
As admin, I want to manage orders | UseCase | Nam, Thăng, Thắng, Tuấn,Quảng | 3 | 3 | 3 | 3 | 3 | 3 | 3
| ERD Diagram | Nam, Thăng, Thắng, Tuấn | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Database design | Nam,Thăng | 3 | 3 | 3 | 3 | 3 | 3 | 3
As admin, I want to manage shipping | UseCase | Nam, Thăng, Thắng, Tuấn,Quảng | 3 | 3 | 3 | 3 | 3 | 3 | 3
| ERD Diagram | Nam, Thăng, Thắng, Tuấn | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Database design | Nam,Thăng | 3 | 3 | 3 | 3 | 3 | 3 | 3
As admin, I want to manage comments | UseCase | Nam, Thăng, Thắng, Tuấn,Quảng | 3 | 3 | 3 | 3 | 3 | 3 | 3
| ERD Diagram | Nam, Thăng, Thắng, Tuấn | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Database design | Nam,Thăng | 3 | 3 | 3 | 3 | 3 | 3 | 3
As customer, I want to see more products. | UseCase | Nam, Thăng, Thắng, Tuấn,Quảng | 3 | 3 | 3 | 3 | 3 | 3 | 3
| ERD Diagram | Nam, Thăng, Thắng, Tuấn | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Database design | Nam,Thăng | 3 | 3 | 3 | 3 | 3 | 3 | 3
As customer, I want to buy products | UseCase | Nam, Thăng, Thắng, Tuấn,Quảng | 3 | 3 | 3 | 3 | 3 | 3 | 3
| ERD Diagram | Nam, Thăng, Thắng, Tuấn | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Database design | Nam,Thăng | 3 | 3 | 3 | 3 | 3 | 3 | 3
As customer, I want to see history order | UseCase | Nam, Thăng, Thắng, Tuấn,Quảng | 3 | 3 | 3 | 3 | 3 | 3 | 3
| ERD Diagram | Nam, Thăng, Thắng, Tuấn | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Database design | Nam,Thăng |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Note on B1: Một chức năng được chia nhỏ ra thành các phần nhỏ hơn gọi là tác vụ. --sinhnx Tue Oct 18 2011 17:33:20 GMT+0700 (SE Asia Standard Time)
Note on C1: Người thực hiện tác vụ này --sinhnx Tue Oct 18 2011 17:33:05 GMT+0700 (SE Asia Standard Time)
Note on D1: Thời gian dự kiến hoàn thành (tính theo giờ) --sinhnx Tue Oct 18 2011 18:18:20 GMT+0700 (SE Asia Standard Time)

## Sprint 3
Hạng mục trong Project Backlog | Công việc trong Sprint | Người thực hiện | Ước tính khối lượng công việc ban đầu | Ước lượng mới về công việc còn lại | [5 empty] | Công việc hiện tại | 314 | 296 | 177.5 | 269 | 311 | 475 | 65
|  |  |  | T2 | T3 | T4 | T5 | T6 | T7 | Thực hiện chuẩn | 314 | 261.6667 | 209.3333 | 157 | 104.6667 | 52.3333 | 0
| Code database | Nam, Thăng | 4 | 1 | 1 | 1 | 1 | 1 | 1
As user, I want to login | Use case description | Nam | 3 | 3 | 3.5 | 3 | 3 | 5 | 0
| Activity Diagram | Nam | 3 | 3 | 3.5 | 3 | 3 | 5 | 0
As user, I wants to logout | Use case description | Nam | 3 | 3 | 3.5 | 3 | 3 | 5 | 0
| Activity Diagram | Nam | 3 | 3 | 3.5 | 3 | 3 | 5 | 0
As customer, I want to registration | Use case description | Nam | 3 | 3 | 3.5 | 3 | 3 | 5 | 0
| Activity Diagram | Nam | 3 | 3 | 3.5 | 3 | 3 | 5 | 0
As user, I want to update information | Use case description | Nam | 3 | 3 | 3.5 | 3 | 3 | 5 | 0
| Activity Diagram | Nam | 3 | 3 | 3.5 | 3 | 3 | 5 | 0
As user, I want to change password | Use case description | Nam | 3 | 3 | 3.5 | 3 | 3 | 5 | 0
| Activity Diagram | Nam | 3 | 3 | 3.5 | 3 | 3 | 5 | 0
As admin, I want to view user | Use case description | Tuấn | 3 | 3 | 0 | 0 | 3 | 5 | 0
| Activity Diagram | Tuấn | 3 | 3 | 0 | 0 | 3 | 5 | 0
As admin, I want to add user | Use case description | Tuấn | 3 | 3 | 0 | 0 | 3 | 5 | 0
| Activity Diagram | Tuấn | 3 | 3 | 0 | 0 | 3 | 5 | 0
As admin, I want to update user | Use case description | Tuấn | 3 | 3 | 0 | 0 | 3 | 5 | 0
| Activity Diagram | Tuấn | 3 | 3 | 0 | 0 | 3 | 5 | 0
As admin, I want to delete user | Use case description | Tuấn | 3 | 3 | 0 | 0 | 3 | 5 | 0
| Activity Diagram | Tuấn | 3 | 3 | 0 | 0 | 3 | 5 | 0
As admin, I want to view customers | Use case description | Tuấn | 3 | 3 | 0 | 0 | 3 | 5 | 0
| Activity Diagram | Tuấn | 3 | 3 | 0 | 0 | 3 | 5 | 0
As admin, I want to search customers | Use case description | Tuấn | 3 | 3 | 0 | 0 | 3 | 5 | 0
| Activity Diagram | Tuấn | 3 | 3 | 0 | 0 | 3 | 5 | 0
As admin, I want to view products | Use case description | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
| Activity Diagram | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
As admin, I want to search products | Use case description | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
| Activity Diagram | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
As admin, I want to add product | Use case description | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
| Activity Diagram | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
As admin, I want to update product | Use case description | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
| Activity Diagram | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
As admin, I want to delete product | Use case description | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
| Activity Diagram | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
As admin, I want to view categories | Use case description | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
| Activity Diagram | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
As admin, I want to add category | Use case description | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
| Activity Diagram | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
As admin, I want to update category | Use case description | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
| Activity Diagram | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
As admin, I want to view brands | Use case description | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
| Activity Diagram | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
As admin, I want to add brand | Use case description | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
| Activity Diagram | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
As admin, I want to update brand | Use case description | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
| Activity Diagram | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
As admin, I want to view order | Use case description | Thăng,Nam | 3 | 3 | 1 | 3 | 3 | 5 | 0
| Activity Diagram | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
As admin, I want to view order details | Use case description | Thăng,Nam | 3 | 3 | 1 | 3 | 3 | 5 | 0
| Activity Diagram | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
As admin, I want to search orders | Use case description | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
| Activity Diagram | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
As admin, I want to update order | Use case description | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
| Activity Diagram | Thăng | 3 | 3 | 1 | 3 | 3 | 5 | 0
As admin, I want to see delivery status | Use case description | Thắng | 3 | 3 | 0.5 | 3 | 3 | 5 | 0
| Activity Diagram | Thắng | 3 | 3 | 0.5 | 3 | 3 | 5 | 0
As admin, I want to cheking ship | Use case description | Thắng | 3 | 3 | 0.5 | 3 | 3 | 5 | 0
| Activity Diagram | Thắng | 3 | 3 | 0.5 | 3 | 3 | 5 | 0
As admin, I want to update cheking | Use case description | Thắng | 3 | 3 | 0.5 | 3 | 3 | 5 | 0
| Activity Diagram | Thắng | 3 | 3 | 0.5 | 3 | 3 | 5 | 0
As admin, I want to view partners | Use case description | Thắng | 3 | 3 | 0.5 | 3 | 3 | 5 | 0
| Activity Diagram | Thắng | 3 | 3 | 0.5 | 3 | 3 | 5 | 0
As admin, I want to add partner | Use case description | Thắng | 3 | 3 | 0.5 | 3 | 3 | 5 | 0
| Activity Diagram | Thắng | 3 | 3 | 0.5 | 3 | 3 | 5 | 0
As admin, I want to update partner | Use case description | Thắng | 3 | 3 | 0.5 | 3 | 3 | 5 | 0
| Activity Diagram | Quảng | 3 | 0 | 0 | 3 | 3 | 5 | 0
As admin, I want to view coments | Use case description | Quảng | 3 | 0 | 0 | 3 | 3 | 5 | 0
| Activity Diagram | Quảng | 3 | 0 | 0 | 3 | 3 | 5 | 0
As admin, I want to active comment | Use case description | Tuấn | 3 | 3 | 0 | 0 | 3 | 5 | 0
| Activity Diagram | Tuấn | 3 | 3 | 0 | 0 | 3 | 5 | 0
As customer, I want to view proucts | Use case description | Nam | 3 | 3 | 3.5 | 3 | 3 | 5 | 0
| Activity Diagram | Nam | 3 | 3 | 3.5 | 3 | 3 | 5 | 0
As customer, I want to view product details | Use case description | Nam | 3 | 3 | 3.5 | 3 | 3 | 5 | 0
| Activity Diagram | Nam | 3 | 3 | 3.5 | 3 | 3 | 5 | 0
As customer, I want to search products | Use case description | Nam | 3 | 3 | 3.5 | 3 | 3 | 5 | 0
| Activity Diagram | Nam | 3 | 3 | 3.5 | 3 | 3 | 5 | 0
As customer, I want to commenting | Use case description | Quảng | 3 | 0 | 0 | 3 | 3 | 5 | 0
| Activity Diagram | Quảng | 3 | 0 | 0 | 3 | 3 | 5 | 0
As customer, I want to view cart | Use case description | Nam,Thăng, Quảng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Activity Diagram | Nam,Thăng, Quảng | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to add product to cart | Use case description | Nam,Thăng, Quảng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Activity Diagram | Nam,Thăng, Quảng | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to change quantity product to cart | Use case description | Nam,Thăng, Quảng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Activity Diagram | Nam,Thăng, Quảng | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to delete product to cart | Use case description | Nam,Thăng, Quảng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Activity Diagram | Nam,Thăng, Quảng | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to confirm order | Use case description | Nam | 3 | 3 | 3.5 | 3 | 3 | 5 | 0
| Activity Diagram | Nam | 3 | 3 | 3.5 | 3 | 3 | 5 | 0
As customer, I want to see history orders | Use case description | Nam | 3 | 3 | 3.5 | 3 | 3 | 5 | 0
| Activity Diagram | Nam | 3 | 3 | 3.5 | 3 | 3 | 5 | 0
As customer, I want to see order details | Use case description | Nam | 3 | 3 | 3.5 | 3 | 3 | 5 | 0
| Activity Diagram | Nam | 3 | 3 | 3.5 | 3 | 3 | 5 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Note on B1: Một chức năng được chia nhỏ ra thành các phần nhỏ hơn gọi là tác vụ. --sinhnx Tue Oct 18 2011 17:33:20 GMT+0700 (SE Asia Standard Time)
Note on C1: Người thực hiện tác vụ này --sinhnx Tue Oct 18 2011 17:33:05 GMT+0700 (SE Asia Standard Time)
Note on D1: Thời gian dự kiến hoàn thành (tính theo giờ) --sinhnx Tue Oct 18 2011 18:18:20 GMT+0700 (SE Asia Standard Time)

## Sprint 4
Hạng mục trong Project Backlog | Công việc trong Sprint | Người thực hiện | Ước tính khối lượng công việc ban đầu | Ước lượng mới về công việc còn lại | [5 empty] | Công việc hiện tại | 784 | 784 | 784 | 784 | 784 | 784 | 784
|  |  |  | T2 | T3 | T4 | T5 | T6 | T7 | Thực hiện chuẩn | 784 | 653.3333 | 522.6667 | 392 | 261.3333 | 130.6667 | 0
As user, I want to login | Model | Nam | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As user, I wants to logout | Model | Nam | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to registration | Model | Nam | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As user, I want to update information | Model | Nam | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As user, I want to change password | Model | Nam | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to view user | Model | Tuấn | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to add user | Model | Tuấn | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to update user | Model | Tuấn | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to delete user | Model | Tuấn | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to view customers | Model | Tuấn | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to search customers | Model | Tuấn | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to view products | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to search products | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to add product | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to update product | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to delete product | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to view categories | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to add category | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to update category | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to view brands | Model | Thắng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to add brand | Model | Thắng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to update brand | Model | Thắng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to view order | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to view order details | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to search orders | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to update order | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to see delivery status | Model | Thắng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to cheking ship | Model | Thắng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to update cheking | Model | Thắng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to view partners | Model | Thắng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to add partner | Model | Thắng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to update partner | Model | Thắng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to view comments | Model | Quảng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to active comment | Model | Tuấn | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to view proucts | Model | Quảng, Nam | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to view product details | Model | Quảng, Nam | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to search products | Model | Nam | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to commenting | Model | Quảng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to view cart | Model | Nam,Thăng, Quảng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to add product to cart | Model | Nam,Thăng, Quảng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to change quantity product to cart | Model | Nam,Thăng, Quảng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to delete product to cart | Model | Nam,Thăng, Quảng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to confirm order | Model | Nam | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to see history orders | Model | Nam | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to see order details | Model | Nam | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
Note on B1: Một chức năng được chia nhỏ ra thành các phần nhỏ hơn gọi là tác vụ. --sinhnx Tue Oct 18 2011 17:33:20 GMT+0700 (SE Asia Standard Time)
Note on C1: Người thực hiện tác vụ này --sinhnx Tue Oct 18 2011 17:33:05 GMT+0700 (SE Asia Standard Time)
Note on D1: Thời gian dự kiến hoàn thành (tính theo giờ) --sinhnx Tue Oct 18 2011 18:18:20 GMT+0700 (SE Asia Standard Time)

## Sprint 5
Hạng mục trong Project Backlog | Công việc trong Sprint | Người thực hiện | Ước tính khối lượng công việc ban đầu | Ước lượng mới về công việc còn lại | [5 empty] | Công việc hiện tại | 784 | 784 | 784 | 784 | 784 | 784 | 784
|  |  |  | T2 | T3 | T4 | T5 | T6 | T7 | Thực hiện chuẩn | 784 | 653.3333 | 522.6667 | 392 | 261.3333 | 130.6667 | 0
As user, I want to login | Model | Nam | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As user, I wants to logout | Model | Nam | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to registration | Model | Nam | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As user, I want to update information | Model | Nam | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As user, I want to change password | Model | Nam | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to view user | Model | Tuấn | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to add user | Model | Tuấn | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to update user | Model | Tuấn | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to delete user | Model | Tuấn | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to view customers | Model | Tuấn | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to search customers | Model | Tuấn | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to view products | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to search products | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to add product | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to update product | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to delete product | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to view categories | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to add category | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to update category | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to view brands | Model | Thắng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to add brand | Model | Thắng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to update brand | Model | Thắng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to view order | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to view order details | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to search orders | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to update order | Model | Thăng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to see delivery status | Model | Thắng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to cheking ship | Model | Thắng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to update cheking | Model | Thắng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to view partners | Model | Thắng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to add partner | Model | Thắng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to update partner | Model | Thắng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to view comments | Model | Quảng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As admin, I want to active comment | Model | Tuấn | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to view proucts | Model | Quảng, Nam | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to view product details | Model | Quảng, Nam | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to search products | Model | Nam | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to commenting | Model | Quảng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to view cart | Model | Nam,Thăng, Quảng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to add product to cart | Model | Nam,Thăng, Quảng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to change quantity product to cart | Model | Nam,Thăng, Quảng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to delete product to cart | Model | Nam,Thăng, Quảng | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to confirm order | Model | Nam | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to see history orders | Model | Nam | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As customer, I want to see order details | Model | Nam | 8 | 8 | 8 | 8 | 8 | 8 | 8
| View |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Controller |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
Note on B1: Một chức năng được chia nhỏ ra thành các phần nhỏ hơn gọi là tác vụ. --sinhnx Tue Oct 18 2011 17:33:20 GMT+0700 (SE Asia Standard Time)
Note on C1: Người thực hiện tác vụ này --sinhnx Tue Oct 18 2011 17:33:05 GMT+0700 (SE Asia Standard Time)
Note on D1: Thời gian dự kiến hoàn thành (tính theo giờ) --sinhnx Tue Oct 18 2011 18:18:20 GMT+0700 (SE Asia Standard Time)

## Sprint6
Hạng mục trong Project Backlog | Công việc trong Sprint | Người thực hiện | Ước tính khối lượng công việc ban đầu | Ước lượng mới về công việc còn lại | [5 empty] | Công việc hiện tại | 20 | 20 | 20 | 20 | 20 | 20 | 20
|  |  |  | T2 | T3 | T4 | T5 | T6 | T7 | Thực hiện chuẩn | 20 | 16.6667 | 13.3333 | 10 | 6.6667 | 3.3333 | 0
| Finish document | Nam | 6 | 6 | 6 | 6 | 6 | 6 | 6
| Make slides, reports | Nam | 6 | 6 | 6 | 6 | 6 | 6 | 6
| Edit the code | Nam, Thăng, Thắng, Quảng, Tuấn | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Note on B1: Một chức năng được chia nhỏ ra thành các phần nhỏ hơn gọi là tác vụ. --sinhnx Tue Oct 18 2011 17:33:20 GMT+0700 (SE Asia Standard Time)
Note on C1: Người thực hiện tác vụ này --sinhnx Tue Oct 18 2011 17:33:05 GMT+0700 (SE Asia Standard Time)
Note on D1: Thời gian dự kiến hoàn thành (tính theo giờ) --sinhnx Tue Oct 18 2011 18:18:20 GMT+0700 (SE Asia Standard Time)

## logs
Date | Developer | Đã làm gì? | Sẽ làm gì? | Gặp khó khăn gì không?
SPRINT 1
15 - 27/10/2019 | Nam, Thăng, Thắng, Tuấn, Quảng | Use case | .A set of necessary use cases describes each use case. | Difficult to identify use cases for the system.
|  | ERD | Detailed description of each entity. | Identify entity.
|  | Entity Relationship Diagram | Draw entity relationship diagram | Determine the relationship
GUI
15 - 27/10/2019 | Nam | Deploying MVC model | Write MVC model code.
SPRINT 2
28-03/11/2019 | Nam, Thăng, Thắng, Tuấn, Quảng | Use case | .A set of necessary use cases describes each use case. | Difficult to identify use cases for the system.
|  | ERD | Detailed description of each entity. | Identify entity.
|  | Entity Relationship Diagram | Draw entity relationship diagram | Determine the relationship
GUI
28-03/11/2019 | Nam | Deploying MVC model | Write MVC model code.
SPRINT 3
04 - 10/11/2019 | Nam, Thăng, Thắng, Tuấn, Quảng | Activity Diagram | Draw Actiity Diagram.
04 - 10/11/2019 | Nam, Thăng, Thắng, Tuấn, Quảng | Sequence Diagram | Draw Sequence Diagram.
04 - 10/11/2019 | Nam, Thăng, Thắng, Tuấn, Quảng | Create database | Write Mysql code based on the entity relationship model model created in sprints 1 and 2, if not suitable, can edit it.
SPRINT 4
11 - 17/11/2019 | Nam, Thăng, Thắng, Tuấn, Quảng | Code View | Using template
11 - 17/11/2019 | Nam, Thăng, Thắng, Tuấn, Quảng | Code Model | Barking and code optimization
11 - 17/11/2019 | Nam, Thăng, Thắng, Tuấn, Quảng | Code Controller | Barking and code optimization
SPRINT 5
18 - 24/11/2019 | Nam, Thăng, Thắng, Tuấn, Quảng | Code View | Using template
18 - 24/11/2019 | Nam, Thăng, Thắng, Tuấn, Quảng | Code Model | Barking and code optimization
18 - 24/11/2019 | Nam, Thăng, Thắng, Tuấn, Quảng | Code Controller | Barking and code optimization
SPRINT 6
25 - 01/12/2019 | Nam | Barking and code optimization | Barking and code optimization
25 - 01/12/2019 | Nam | Finish document and doing report

## Project-info
Đề tài: | VTC Store
Wedbsite address: | vtcstore.com
Độ dài Sprint: | 1 tuần
Số ngày làm việc: | 6 ngày
Thành viên
Mã SV | Họ và tên | Chức danh | Số ngày có mặt trong Sprint | Số giờ có mặt trong ngày | Tổng số giờ có mặt
NDE18011 | Ngô Đức Nam | Developer | 6 | 5 | 180
NDE18074 | Nguyễn Trung Thăng | Developer | 6 | 5 | 180
NDE18091 | Lý Bảo Thắng | Developer | 5 | 5 | 150
NDE18037 | Ngô Anh Tuấn | Developer | 5 | 5 | 150
NDE18082 | Nguyễn Quốc Quảng | Developer | 4 | 5 | 120